## Defect_tracker
SI No | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status (Open/Closed) | Remarks
1 | 2026-02-05 | Missing and null values found in raw dataset affecting preprocessing | Sprint 1 | Backend Team | Data Issue | Applied imputation techniques and cleaned dataset | 2026-02-07 | Closed | Data preprocessing completed successfully
2 | 2026-02-08 | Inconsistent date format causing errors in time-based analysis | Sprint 1 | Backend Team | Data Issue | Standardized date column to datetime format | 2026-02-09 | Closed | Date format issue resolved
3 | 2026-02-12 | Outliers impacting demand trend analysis during EDA | Sprint 1 | Backend Team | Analysis Issue | Removed outliers using IQR method | 2026-02-13 | Closed | Data ready for analysis
4 | 2026-02-17 | Improper feature scaling affecting model input data | Sprint 2 | Backend Team | Preprocessing | Applied normalization and standardization techniques | 2026-02-18 | Closed | Feature scaling corrected
5 | 2026-02-20 | Irrelevant features reducing model performance | Sprint 2 | Backend Team | Model Issue | Performed feature selection using correlation analysis | 2026-02-22 | Closed | Model performance improved
6 | 2026-02-25 | Data leakage observed between training and testing datasets | Sprint 2 | Backend Team | Model Training | Separated datasets properly and re-trained model | 2026-02-26 | Closed | Valid training ensured
7 | 2026-03-05 | Model overfitting on training data leading to poor generalization | Sprint 3 | Backend Team | Model Training | Applied cross-validation and regularization techniques | 2026-03-07 | Closed | Model generalized well
8 | 2026-03-10 | Prediction accuracy lower than expected on validation data | Sprint 3 | Backend Team | Model Issue | Performed hyperparameter tuning | 2026-03-12 | Closed | Accuracy improved
9 | 2026-03-18 | FastAPI /predict endpoint returning incorrect response format | Sprint 4 | Backend Team | Integration | Fixed API response schema and validated output format | 2026-03-20 | Closed | API functioning correctly
10 | 2026-03-22 | Batch prediction script failing for new input dataset | Sprint 4 | Backend Team | Script Issue | Updated script to handle new CSV structure | 2026-03-24 | Closed | Batch prediction working